## Sheet1
Ex. Pole # | New Pole # | Circuit (Top) | Work Type | Const Comp | New Pole Type | Const Comp. | W/O # | GPS |  |  | Rem | Repl | QC Date
FEBRUARY
7545BV | 15301BV | Bear City | REPLACE | 2022-02-01 | 45'CL 1 | IZ | NA | 34.2679559, -116.8586448 |  | 1027 Bear MTN |  | 1
63101CTC |  | Erwin | REMIDIATE |  |  | OS |  |  |  |  | 1
9518BV |  | Erwin | REMIDIATE |  |  | OS |  |  |  |  | 1
9519BV |  | Erwin | REMIDIATE |  |  | OS |  |  |  |  | 1
62992CTC |  | Erwin | REMIDIATE |  |  | OS |  |  |  |  | 1
9032BV |  | Erwin | REMIDIATE |  |  | OS |  |  |  |  | 1
9637BV |  | Erwin | REMIDIATE |  |  | OS |  |  |  |  | 1
7723BV |  | Erwin | REMIDIATE |  |  | OS |  |  |  |  | 1
9635BV |  | Erwin | REMIDIATE |  |  | OS |  |  |  |  | 1
10781BV |  | Erwin | REMIDIATE |  |  | OS |  |  |  |  | 1
11631BV |  | Erwin | REMIDIATE |  |  | OS |  |  |  |  | 1
8201BV |  | Erwin | REMIDIATE |  |  | OS |  |  |  |  | 1
9139BV |  | Erwin | REMIDIATE |  |  | OS |  |  |  |  | 1
MARCH
8055BV |  | Clubview | REPLACE | 2022-03-01 | 45' CL1 COMP | IZ | 60400089 | 34.23647529, -116.877460766 |  | 42365 Switzerland |  | 1
8056BV |  | Clubview | REPLACE | 2022-03-01 | 45' CL1 COMP | IZ | 60400089 | 34.236, -116.87745 |  | 42499 Bristlecone |  | 1
23946CIT |  | Sunset | REMIDIATE | 2022-03-01 |  | IZ | 60400090 | 34.2395700, -116.8349478 |  | 683 Kern | 1
23945CIT |  | Sunset | REMIDIATE | 2022-03-01 |  | IZ | 60400090 | 34.2401318, -116.8349304 |  | 683 Kern | 1
|  | Erwin | REPLACE | 2022-03-12 | LWS | BVES | [5 empty] | 1
|  | Boulder | REPLACE | 2022-03-19 | Composite | BVES | [5 empty] | 2
|  | Baldwin | REPLACE | 2022-03-26 | LWS | OS | [5 empty] | 10
|  | Boulder | New Poles | 2022-03-19 | Composite | BVES | [5 empty] | 10
APRIL
7521BV | 14923BV | Castle Glen | REPLACE | 2022-04-01 | 40' COMP | IZ | 60400070 | 34.2532956, -116.8650757 |  | 508 Pine Wood Ct |  | 1
7520BV |  | Castle Glen | REMIDIATE | 2022-04-01 |  | IZ | 60400070 | 34.2533050, -116.8657103 |  | 508 Pine Wood Ct | 1
7518BV |  | Castle Glen | REMIDIATE | 2022-04-01 |  | IZ | 60400070 | 34.2526923, -116.8657735 |  | 508 Pinewood Ct | 1
9889BV |  | Paradise | REMIDIATE | 2022-04-01 |  | IZ | NA | 34.2576152,-116.8492743 |  | 509 Sawmill | 1
10816BV |  | Paradise | REMIDIATE | 2022-04-01 |  | IZ | NA | 34.2580699,-116.8489985 |  | 509 Sawmill | 1
4052BV |  | Paradise | REMIDIATE | 2022-04-01 |  | IZ | 60400074 | 34.2584622, -116.8505770 |  | 326 W Rainbow | 1
10000BV |  | Paradise | REMIDIATE | 2022-04-01 |  | IZ | 60400074 | 34.2584050, -116.8508982 |  | 326 W Rainbow | 1
10001BV |  | Paradise | REMIDIATE | 2022-04-01 |  | IZ | 60400074 | 34.2588283,-116.8509028 |  | 326 W Rainbow | 1 |  | 2022-08-24
|  | Country Club | REPLACE | 2022-04-02 | Composite | BVES | [5 empty] | 1
7520BV | 15310BV | Castel Glen | REPLACE | 2022-04-02 | Composite | BVES | [5 empty] | 1
10999BV | 14847BV | Baldwin | REPLACE | 2022-04-02 | Wood | OS | [5 empty] | 1 | 2022-04-19
10998BV | 14840BV | Baldwin | REPLACE | 2022-04-09 | LWS | OS | [5 empty] | 1 | 2022-04-20
5688BV | 13311BV | Boulder | REPLACE | 2022-04-09 | LWS | BVES | 40411959 | 34.22992,-116.93930 |  |  |  | 1 | 2022-05-01
5132BV | 13310BV | Boulder | REPLACE | 2022-04-09 | LWS | BVES | 40411959 | 34.22951,-116.93917 |  |  |  | 1 | 2022-04-28
10997BV | 14844BV | Baldwin | REPLACE | 2022-04-16 | LWS | OS | [5 empty] | 1 | 2022-04-20
10995BV | 14845BV | Baldwin | REPLACE | 2022-04-16 | LWS | OS | [5 empty] | 1 | 2022-04-20
10993BV | 14836BV | Baldwin | REPLACE | 2022-04-16 | LWS | OS | [5 empty] | 1 | 2022-04-20
10992BV | 14846BV | Baldwin | REPLACE | 2022-04-16 | LWS | OS | [5 empty] | 1 | 2022-04-20
10990BV | 14838BV | Baldwin | REPLACE | 2022-04-16 | LWS | OS | [5 empty] | 1 | 2022-04-20
10989BV | 14849BV | Baldwin | REPLACE | 2022-04-16 | LWS | OS | [5 empty] | 1 | 2022-04-20
5126BV | 13307BV | Boulder | REPLACE | 2022-04-16 | LWS | BVES | 40411959 | 34.22954,-116.94232 |  |  |  | 1 | 2022-04-15
|  | Boulder | REPLACE | 2022-04-23 | Wood | BVES | [5 empty] | 1
4185BV | 13301BV | Boulder | REPLACE | 2022-04-23 | LWS | BVES | 40411959 | 34.23193,-116.94227 |  |  |  | 1 | 2022-04-25
4190BV | 13306BV | Boulder | REPLACE | 2022-04-23 | LWS | BVES | 40411959 | 34.23021,-116.94278 |  |  |  | 1 | 2022-04-25
10751BV |  | Baldwin | REMEDIATE | 2022-04-30 |  | OS |  |  |  |  | 1 |  | 2022-05-01
5699BV |  | Boulder | REMEDIATE | 2022-04-30 |  | BVES | 40411959 | 34.23042,-116.93933 |  |  | 1
MAY
10978BV | 15276BV | CLUBVIEW | REPLACE | 2022-05-01 | Composite | SD | 60400097 | 34.23985395, -116.8727001389 |  |  |  | 1
9385BV | XXXXXXX | CLUBVIEW | REMEDIATE | 2022-05-01 |  | SD | 60400097 | 34.240158, -116.874394 |  |  | 1
5129BV | 13309BV | Boulder | REPLACE | 2022-05-06 | Wood | BVES | 40411959 | 34.22949,- 116.94079 |  |  |  | 1 | 2022-05-07
4186BV | 13302BV | Boulder | REPLACE | 2022-05-06 | Composite | BVES | 40411959 | 34.23160,-116.94254 |  |  |  | 1 | 2022-05-01
5128 |  | Baldwin | REMEDIATE | 2022-05-06 |  | BVES | 40411959 | 34.22937,-116.94128 |  |  | 1
4187BV | 13303BV | Boulder | REPLACE | 2022-05-21 | Wood | BVES | 40411959 | 34.23124,-116.94278 |  |  |  | 1 | 2022-06-19
4188BV | 13304BV | Boulder | REPLACE | 2022-05-21 | Wood | BVES | 40411959 | 34.23077,-116.94280 |  |  |  | 1 | 2022-06-19
4189BV | 13305BV | Boulder | REPLACE | 2022-05-21 | Composite | BVES | 40411959 | 34.23072,-116.94270 |  |  |  | 1 | 2022-06-20
10862BV |  | Goldmine | REMEDIATE | 2022-05-21 |  | IZ | 60400095 | 34.2576152, -116.8492743 |  |  | 1
10863BV |  | Goldmine | REMEDIATE | 2022-05-21 |  | IZ | 60400095 | 34.2346185, -116.8586270 |  |  | 1
June
62919CTC | 15278BV | CASTLE GLEN | REPLACE | 2022-06-08 |  | SD |  | 34.2610868167, -116.8660707722 |  | 1140 Aeroplane |  | 1
JULY
3585BV | 15320BV | CLUBVIEW | REPLACE | 2022-07-01 | Wood | IZ |  | 34.2277865, -116.8656508 |  | 1223 Aspen |  | 1
8604CIT | 14888BV | VILLAGE | REPLACE | 2022-07-01 | Wood | IZ |  | 34.2404827,-116.9125415 |  | Bartlett EV |  | 1
11654BV | 15175BV | Holcomb | REPLACE | 2022-07-05 | Composite | BVES | 60400094 | 34.16635,-116.51139 |  | 365 N. Shore Dr |  | 1
11616BV | 15167BV | Holcomb | REPLACE | 2022-07-06 | Wood | BVES | 60400094 | 34.16153,-116.50453 |  | 101 E. North Shore |  | 1
10025BV | 14631BV | SHAY 34KV | REPLACE | 2022-07-11 | LWS | OS | 60400008 | 34.259793,-116.842083 |  | 252 E. SHERWOOD |  | 1 | 2022-09-13
BV11105 | 14627BV | SHAY 34KV | REPLACE | 2022-07-11 | LWS | OS | 60400008 | 34.259658,-116.839941 |  | 344 E. SHERWOOD |  | 1 | 2022-09-13
10019BV | 14637bv | Shay 34kV | REPLACE | 2022-07-12 | Wood | OS | 60400008 | 34.25977,-116.84479 |  | 112 sherwood |  | 1 | 2022-09-24
10018BV | 14638bv | Shay 34kV | REPLACE | 2022-07-12 | Wood | OS | 60400008 | 34.25979,-116.84517 |  | 106 sherwood |  | 1 | 2022-09-14
10016BV | 14640bv | Shay 34kV | REPLACE | 2022-07-12 | Wood | OS | 60400008 | 34.25979,-116.84598 |  | 108 w. sherwood |  | 1 | 2022-09-13
10015BV | 14641bv | Shay 34kV | REPLACE | 2022-07-12 | Wood | OS | 60400008 | 34.25978,-116.84645 |  | 116 w sherwood |  | 1 | 2022-09-13
10014BV | 14642bv | Shay 34kV | REPLACE | 2022-07-13 | Wood | OS | 60400008 | 34.25976,-116.84686 |  | 128 w. sherwood |  | 1 | 2022-09-14
10020BV | 14636bv | Shay 34kV | REPLACE | 2022-07-13 | Wood | OS | 60400008 | 34.2598,-116.844381 |  | 124 W. SHERWOOD |  | 1 | 2022-09-14
9983BV | 14986BV | Shay | Replacement | 2022-07-13 | Wood | OS | 60400008 | 34.152708,-116.513069 |  | 724 Sugarloaf BLVD |  | 1 | 2022-09-16
10008BV | 14645BV | SHAY 34KV | REPLACE | 2022-07-14 | Wood | OS | 60400008 | 34.25979,-116.8478 |  | 208 w. sherwood |  | 1 | 2022-09-13
10017BV | 14639bv | Shay 34kV | REPLACE | 2022-07-15 | Wood | OS | 60400008 | 34.25977,-116.84554 |  | 100 e sherwood |  | 1 | 2022-09-13
6638BV | 15166BV | Pioneer | REPLACE | 2022-07-16 | LWS | BVES | 60400094 | 34.161939, -116.502699 |  | 1099 Pan Springs Ln. |  | 1
10013bv | 14643bv | Shay 34kV | REPLACE | 2022-07-19 | Wood | OS | 60400008 | 34.25976, 116.84732 |  | 136 w sherwood |  | 1 | 2022-09-24
10012bv | 14644bv | Shay 34kV | REPLACE | 2022-07-20 | Wood | OS | 60400008 | 34.25977, -116.84752 |  | 200 W SHERWOOD |  | 1 | 2022-09-24
10007bv | 14646BV | Shay 34kV | REPLACE | 2022-07-21 | Wood | OS | 60400008 | 34.25977, -116.84962 |  | 316 W SHERWOOD |  | 1 | 2022-09-24
10006BV | 14647BV | Shay 34kV | REPLACE | 2022-07-21 | Wood | OS | 60400008 | 34.25976, -116.85006 |  | 324 W. SHERWOOD |  | 1 | 2022-09-24
10005BV | 14648BV | Shay 34kV | REPLACE | 2022-07-21 | Wood | OS | 60400008 | 34.25973, -116.85035 |  | 336 W. SHERWOOD |  | 1 | 2022-09-24
10004BV | 14649BV | Shay 34kV | REPLACE | 2022-07-21 | Wood | OS | 60400008 | 34.25975, -116.85088 |  | 344 W. SHERWOOD |  | 1 | 2022-09-13
10003BV | 14975BV | Shay 34kV | REPLACE | 2022-07-21 | Wood | OS | 60400008 | 34.25975, -116.85088 |  | 301-399 S PINON DR |  | 1 | 2022-09-13
10000BV | 14976BV | Shay 34kV | REPLACE | 2022-07-22 | Wood | OS | 60400008 | 34.25975, -116.85088 |  | 336 W RAINBOW BLVD |  | 1
9999BV | 14977BV | Shay 34kV | REPLACE | 2022-07-22 | Wood | OS | 60400008 | 34.25813, -116.8509 |  | 535 S. PINON DR |  | 1 | 2022-08-24
9998BV | 14978BV | Shay 34kV | REPLACE | 2022-07-22 | Wood | OS | 60400008 | 34.25777, -116.85089 |  | 312 SUGARLOAF BLVD |  | 1 | 2022-09-13
10011BV |  | Shay | REMEDIATE | 2022-07-30 |  | OS | 60400008 | 34.153511, -116.505244 |  |  | 1 |  | 2022-09-24
10020BV | 14636bv | Shay 34kV | REPLACE | 2022-07-13 | Wood | OS | 60400008 | 34.2598,-116.844381 |  | 124 W. SHERWOOD |  | 1 | 2022-09-14
9984BV | 14985BV | Shay | Replacement | 2022-07-22 | Wood | OS | 60400008 | 34.152801,-116.512962 |  | 712 Sugarloaf BLVD. |  | 1 | 2022-10-04
9985BV | 14984BV | Shay | Replacement | 2022-07-22 | Wood | OS | 60400008 | 34.152879,-116.512810 |  | 708 Sugarloaf BLVD. |  | 1 | 2022-09-16
9987BV | 14983BV | Shay | Replacement | 2022-07-22 | Wood | OS | 60400008 | 34.152783,-116.512483 |  | 640 Sugarloaf BLVD. |  | 1 | 2022-09-14
9979BV | 14989BV | Castle Glen 4kV | Replacement | 2022-08-03 | Wood | OS | 60400008 | 34 15 27.93 | -1165137.05 |  |  | 1 | 2022-08-09
AUGUST
9978BV | 14990BV | Castle Glen 4kV | Replacement | 2022-08-03 | Wood | OS | 60400008 | 34 15 27.94 | -1165139.15 |  |  | 1 | 2022-08-21
9996BV |  | Castle Glen 4kV | Remediation | 2022-08-03 |  | OS | 60400008 | 34 15 27.95 | -1165107.18 |  | 1 |  | 2022-08-24
9997BV |  | Country Club 4kV | Remediation | 2022-08-03 |  | OS | 60400008 | 34 15 27.96 | -1165105.68 |  | 1 |  | 2022-08-24
9994BV |  | Country Club 4kV | Remediation | 2022-08-03 |  | OS | 60400008 | 34 15 27.91 | -1165112.71 |  | 1 |  | 2022-08-24
13036BV |  | Castle Glen 4kV | Remediation | 2022-08-02 |  | OS | 60400008 | 34 15 28.08 | -1165153 |  | 1 |  | 2022-08-29
9968BV | 14997BV | Castle Glen 4kV | Replacement | 2022-08-01 | Wood | OS | 60400008 | 34 15 28.08 | -1165154.83 |  |  | 1 | 2022-08-09
9979BV | 14989BV | Castle Glen 4kV | Replacement | 2022-08-03 | Wood | OS | 60400008 | 34 15 27.93 | -1165137.05 |  |  | 1 | 2022-08-09
9977BV | 14991BV | Castle Glen 4kV | Replacement | 2022-08-03 | Wood | OS | 60400008 | 34 15 27.93 | -1165140.5 |  |  | 1 | 2022-08-09
10088BV | 14980BV | Castle Glen 4kV | Replacement | 2022-08-03 | Wood | OS | 60400008 | 34 15 27.93 | -1165108.84 |  |  | 1 | 2022-08-24
9986BV |  | Country Club 4kV | Remediation | 2022-08-01 |  |  | 60400008 | 34 15 28.37 | -1165126.62 |  | 1 |  | 2022-08-24
9988bv | 14982bv | Shay 34kV | Replacement | 2022-08-01 | Wood | BVES | 60400008 | 34 15 27.87 | - 116 51 21.82 |  |  | 1 | 2022-09-16
9989bv | 14981bv | Shay 34kV | Replacement | 2022-08-05 | Wood | BVES | 60400008 | 34 15 27.82 | - 116 51 21.82 |  |  | 1 | 2022-08-24
9970bv | 14996bv | Shay 34kV | Replacement | 2022-08-05 | Wood | BVES | 60400008 | 34 15 28.00 | - 116 51 51.31 |  |  | 1 | 2022-09-16
9971bv | 14995bv | Shay 34kV | Replacement | 2022-08-05 | Wood | BVES | 60400008 | 34 15 28.02 | - 116 51 49.71 |  |  | 1 | 2022-10-01
10081bv | 14979bv | Shay 34kV | Replacement | 2022-08-05 | Wood | BVES | 60400008 | 34 15 26.66 | - 116 51 03.14 |  |  | 1
60490CIT | 15163BV | Holcomb | Replacement | 2022-08-13 | LWS | BVES | 60400008 | 34.161443,-116.505216 |  | 1113 Myrtle Ave |  | 1
60700CIT | 15154BV | Holcomb | Replacement | 2022-08-13 | LWS | BVES | 60400008 | 34.160018,-116.510098 |  | 924 Peter Ave |  | 1
8226BV | 15165BV | Holcomb | Replacement | 2022-08-13 | LWS | BVES | 60400008 | 34.161545,-116.503224 |  | 1088 Hugo Ln. |  | 1
9976BV | 14992BV | Shay | Replacement | 2022-08-09 | Wood | OS | 60400008 | 34.152767,-116.514263 |  | 524 Sugarloaf BLVD. |  | 1 | 2022-09-16
9975BV | 14993BV | Shay | Replacement | 2022-08-09 | Wood | OS | 60400008 | 34.152799,-116.514427 |  | 1000 Sugarloaf BLVD. |  | 1 | 2022-09-14
9982BV | 14987BV | Shay | Replacement | 2022-08-10 | Wood | OS | 60400008 | 34.152788,-116.513210 |  | 732 Sugarloaf BLVD. |  | 1 | 2022-09-16
9983BV | 14986BV | Shay | Replacement | 2022-08-10 | Wood | OS | 60400008 | 34.152708,-116.513069 |  | 724 Sugarloaf BLVD |  | 1 | 2022-09-16
9967BV | 14998BV | Shay | Replacement | 2022-08-11 | Wood | OS | 60400008 | 34.152806,-116.515660 |  | 1132 Sugarloaf BLVD |  | 1 | 2022-08-09
31734CIT | 15003BV | Shay | Replacement | 2022-08-18 | LWS | OS | 60400008 | 34.154502,-116.515847 |  | Across from 312 Division |  | 1
10123BV | 15047BV | Shay | Replacement | 2022-08-17 | Wood | OS | 60400008 | 34.144321,-116.515830 |  | 840 McAlister |  | 1 | 2022-11-21
CTC62952 | 15004BV | Shay | Replacement | 2022-08-18 | LWS | OS | 60400008 | 34.154383,-116.515845 |  | Across from 303 Division |  | 1
10370BV | 15005BV | Shay | Replacement | 2022-08-18 | Wood | OS | 60400008 | 34.154268,-116.515857 |  | Across from 1137 W Country Club |  | 1
8905BV | 15028BV | Shay | Replacement | 2022-08-19 | Wood | OS | 60400008 | 34.151014,-116.515942 |  | 548 Division |  | 1 | 2022-10-01
8906BV | 15029BV | Shay | Replacement | 2022-08-19 | Wood | OS | 60400008 | 34.150883,-116.515911 |  | 552 Division |  | 1 | 2022-10-04
8907BV | 15030BV | Shay | Replacement | 2022-08-19 | Wood | OS | 60400008 | 34.150747,-116.515940 |  | 566 Division |  | 1 | 2022-10-04
31695CIT | 15006BV | Shay | Replacement | 2022-08-20 | Wood | OS | 60400008 | 34.154131,-116.515845 |  | Across from 208 Division |  | 1
8072BV | 15162BV | Castle Glen | Replacement | 2022-08-20 | Wood | BVES | 60400094 | 34.145843,-116.523806 |  | 140 Silverpeck RD |  | 1
1557BV | 15156BV | Castle Glen | Replacement | 2022-08-20 | Wood | BVES | 60400094 | 34.153069,-116.514757 |  | 1025 Rainbow |  | 1
7562BV | 15155BV | Holcomb | Replacement | 2022-08-20 | Wood | BVES | 60400094 | 34.160415,-116.513240 |  | 1027 Whispering Forest Dr. |  | 1
10001BV |  | Paradise 4kV | Remediation |  |  | OS | 60400008 | 34 15 37.73 | -1165103.19 |  | 1 |  | 2022-08-24
10002BV |  | Paradise 4kV | Remediation |  |  | OS | 60400008 | 34 15 33.06 | -1165103.18 |  | 1 |  | 2022-08-24
9999BV | 14977BV | Paradise 4kV | Replacement |  | Wood | OS | 60400008 | 34 15 29.28 | -1165103.13 |  |  | 1 | 2022-08-24
9990BV |  |  | Remediation |  |  | OS | 60400008 | 34 15 27.86 | -1165120 |  | 1 |  | 2022-08-24
9993BV |  | Country Club 4kV | Remediation |  |  | OS | 60400008 | 34 15 27.89 | -1165114.65 |  | 1 |  | 2022-08-24
9992BV |  | Country Club 4kV | Remediation |  |  | OS | 60400008 | 34 15 27.89 | -1165116.22 |  | 1 |  | 2022-08-24
9991BV |  | Country Club 4kV | Remediation |  |  | OS | 60400008 | 34 15 27.86 | -1165118.21 |  | 1 |  | 2022-08-24
9995BV |  | Country Club 4kV | Remediation |  |  | OS | 60400008 | 34 15 27.95 | -1165110.79 |  | 1 |  | 2022-08-24
9978BV | 14990BV | Castle Glen 4kV | Replacement |  |  | OS | 60400008 | 34 15 27.94 | -1165139.15 |  |  | 1 | 2022-08-21
9973BV |  | Castle Glen 4kV | Remediation |  |  | OS | 60400008 | 34 15 28.00 | -1165146.61 |  | 1 |  | 2022-08-24
9972BV |  | Castle Glen 4kV | Remediation |  |  | OS | 60400008 | 34 15 28.02 | -1165148.37 |  | 1 |  | 2022-08-24
8904BV | 15027BV | shay | Replacement | 2022-08-22 | LWS | OS | 60400008 | 34 15 11.45 | w-116 51 59.71 | 535 divison |  | 1
13198BV |  | shay | Remediation | 2022-08-22 | Wood | OS | 60400008 | 34 15 12.33 | w-116 51 59.05 | 521 divison | 1 |  | 2022-10-04
8902BV | 15026BV | shay | Replacement | 2022-08-22 | Wood | OS | 60400008 | 34 15 12.69 | w-116 51 58.48 | 501 divison |  | 1 | 2023-01-05
8915BV | 15036BV | shay | Replacement | 2022-08-24 | Wood | OS | 60400008 | 34 14 58.30 | w-116 51 58.20 | 650 mcalister |  | 1 | 2022-11-21
8911BV | 15034BV | shay | Replacement | 2022-08-24 | Wood | OS | 60400008 | 34 15 03.04 | w-116 51 58.08 | 615 mcalister |  | 1 | 2022-11-22
n/a | 15052BV | shay | Replacement | 2022-08-24 | Wood | OS | 60400008 | 34 15 06.20 | w-116 51 56.24 | 574 pinewood |  | 1
12930BV |  | shay | Remediation | 2022-08-25 |  | OS | 60400008 | 34 15 03.04 | w-116 51 58.08 | 626 mcalister | 1 |  | 2022-11-21
12929BV |  | shay | Remediation | 2022-08-25 |  | OS | 60400008 | 34 15 01.12 | w-116 51 58.10 | 626 mcalister | 1 |  | 2022-11-21
8916BV | 15037BV | shay | Replacement | 2022-08-25 | Wood | OS | 60400008 | 34 14 57.47 | w-116 51 58.26 | mcalister and redwood |  | 1 | 2022-11-21
8917BV | 15038BV | shay | Replacement | 2022-08-25 | Wood | OS | 60400008 | 34 14 55.77 | w-116 51 58.39 | mcalister and redwood |  | 1 | 2022-12-01
14556BV |  | shay | Remediation | 2022-08-25 |  | OS | 60400008 | 34 14 49.54 | w-116 51 58.25 | 730 mcalister | 1 |  | 2022-11-21
10120BV | 15044BV | shay | Replacement | 2022-08-25 | Wood | OS | 60400008 | 34 14 47.96 | w-116 51 58.27 | 760 mcalister |  | 1 | 2022-11-21
10123BV | 15047BV | Shay | Replacement | 2022-09-17 | Wood | OS | 60400008 | 34.144321,-116.515830 |  | 840 McAlister
SEPTEMBER
8910BV | 15033BV | Shay | Replacement | 2022-09-01 | Wood | OS | 60400008 | 34.150531,-116.515803 |  |  |  |  | 2022-11-21
6017BV | 15095BV | Erwin 4kv | Replacement | 2022-09-11 | LWS | BVES | 28201 Car Hit Pole | 34.250887,-116.816033 |  | HWY 38 N/O Baldwin Ln |  | 1 | 2022-11-20
BV11116 | 15016BV | Shay | Replacement | 2022-09-13 | Wood | OS | 60400008 | 34.152513,-116.515853 |  | 42897 Timberline TRL |  | 1
10127BV | 15051BV | Shay | Replacement | 2022-09-13 | Wood | OS | 60400008 | 34.143675,-116.515844 |  | 970 McAlister |  | 1 | 2022-11-21
CIT37191 | 15017BV | Shay | Replacement | 2022-09-16 | Wood | OS | 60400008 | 34.152307,-116.515815 |  | 400 Division |  | 1 | 2022-10-01
CTC1211668 | 15020BV | Shay | Replacement | 2022-09-16 | Wood | OS | 60400008 | 34.152032,-116.515805 |  | 410 Division |  | 1
10123BV | 15047BV | Shay | Replacement | 2022-09-17 | Wood | OS | 60400008 | 34.144321,-116.515830 |  | 840 McAlister |  | 1
10124BV | 15048BV | Shay | Replacement | 2022-09-17 | Wood | OS | 60400008 | 34.144164,-116.515832 |  | 850 McAlister |  | 1 | 2022-11-21
5292BV | 15322BV | Goldmine 4kv | Replacement | 2022-09-17 | Composite | BVES | 60400106 | 34.225783,-116.855550 |  | 1410 Rockspray |  | 1
7302BV | 14906BV | Clubview 4kv | Replacement | 2022-09-17 | Composite | BVES | 60400107 | 34.238969,-116.854777 |  | 1242 Minton |  | 1
5291BV | 15318BV | Goldmine 4KV | Replacement | 2022-09-21 | Composite | BVES | 60400106 | 34.226272,-116.855305 |  | Isaiah Z. 1405 Rockspray |  | 1
62465CTC | 15159BV | Castle Glen 4KV | Replacement | 2022-09-22 | Wood | BVES | 60400094 | 34.152957,-116.870790 |  | Intrusive design 149 Winding way |  | 1
9255BV | 15129BV | Clubview 4KV | Replacement | 2022-09-24 | Composite | BVES | 60400123 | 34.234528,-116.870790 |  | Sherri D Birch St/Falcon Ave |  | 1
8914BV | 15035BV | Shay 34kv | Replacement | 2022-09-19 | Wood | OUCC | 60400008 | 34.145937,-116.515815 |  | 650 McAlister |  | 1 | 2022-11-22
10118BV | 15043BV | Shay 34kv | Replacement | 2022-09-19 | Wood | OUCC | 60400008 | 34.145130,-116.515833 |  | 751 McAlister |  | 1 | 2022-11-21
62477CTC | 15042BV | Shay 34kv | Replacement | 2022-09-19 | Wood | OUCC | 60400008 | 34.145286,-116.515842 |  | 701 McAlister |  | 1
62487BV | 15053BV | Shay 34kv | Replacement | 2022-09-23 | Wood | OUCC | 60400008 | 34.143590,-116.515842 |  | 980 McAlister |  | 1 | 2022-11-21
10227BV | 15079BV | Shay 34kv | Replacement | 2022-09-23 | Wood | OUCC | 60400008 | 34.142070,-116.522872 |  | 712 Elm |  | 1 | 2022-12-28
10226BV | 15080BV | Shay 34kv | Replacement | 2022-09-23 | Wood | OUCC | 60400008 | 34.141946,-116.522869 |  | 742 Elm |  | 1 | 2023-12-28
10225BV | 15081BV | Shay 34kv | Replacement | 2022-09-23 | Wood | OUCC | 60400008 | 34.141847,-116.522864 |  | 750 Elm |  | 1 | 2022-12-28
10228BV | 15078BV | Shay 34kv | Replacement | 2022-09-24 | Wood | OUCC | 60400008 | 34.142228,-116.522886 |  | 694 Elm |  | 1 | 2022-12-28
10229BV | 15077BV | Shay 34kv | Replacement | 2022-09-24 | Wood | OUCC | 60400008 | 34.142407,-116.522887 |  | 674 Elm |  | 1 | 2022-12-28
10230BV | 15076BV | Shay 34kv | Replacement | 2022-09-24 | Wood | OUCC | 60400008 | 34.142579,-116.522879 |  | 640 Elm |  | 1 | 2022-12-28
10345BV | 15007BV | Shay 34kv | Replacement | 2022-09-26 | LWS | OUCC | 60400008 | 34.153993,-116.515849 |  | Division/Aeroplane dr |  | 1
8689BV | 15008BV | Shay 34kv | Replacement | 2022-09-26 | LWS | OUCC | 60400008 | 34.153892,-116.515846 |  | Division/ Aeroplane Dr. |  | 1
10126BV | 15050BV | Shay 34kv | Replacement | 2022-09-26 | Wood | OUCC | 60400008 | 34.143843,-116.515834 |  | 920 McAlister |  | 1 | 2022-11-21
10125BV | 15049BV | shay 34kv | Replacement | 2022-09-26 | Wood | OUCC | 60400008 | 34.144008,-116.515833 |  | 902 McAlister |  | 1 | 2022-11-21
10121BV | 15045BV | Shay 34kv | Replacement | 2022-09-27 | Wood | OUCC | 60400008 | 34.144639,-116.515831 |  | 802 McAlister |  | 1 | 2022-11-21
10122BV | 15046BV | Shay 34kv | Replacement | 2022-09-27 | Wood | OUCC | 60400008 | 34.144481,-116.515829 |  | 802 McAlister |  | 1 | 2022-11-21
10223BV | 15083BV | Shay 34kv | Replacement | 2022-09-28 | Wood | OUCC | 60400008 | 34.141605,-116.522860 |  | 794 Elm |  | 1 | 2022-12-28
10222BV | 15084BV | Shay 34kv | Replacement | 2022-09-28 | Wood | OUCC | 60400008 | 34.141508,-116.522856 |  | 804 Elm |  | 1 | 2022-12-28
8918BV | 15041BV | Shay 34kv | Replacement | 2022-09-29 | LWS | OUCC | 60400008 | 34.145407,-116.515857 |  | 701 McAlister |  | 1
8939BV | 15039BV | Shay 34kv | Replacement | 2022-09-29 | Wood | OUCC | 60400008 | 34.145459,-116.515978 |  | 802 McAlister |  | 1
8940BV | 15040BV | Shay 34kv | Replacement | 2022-09-29 | Wood | OUCC | 60400008 | 34.145465,-116.520156 |  | 802 McAlister |  | 1 | 2022-11-21
10224BV | 15082BV | Shay 34kv | Replacement | 2022-09-30 | Wood | OUCC | 60400008 | 34.141705,-116.522860 |  | 794 Elm |  | 1 | 2022-12-28
4954BV | 15160BV | Paradise 4kv | Replacement | 2022-09-27 | Wood | OUCC | 60400094 | 34.153784,-116.505550 |  | 229 W. Mojave BLVD |  | 1
8902BV | 15026BV | shay | Replacement | 2022-09-27 | Wood | OUCC | 60400008 | 34 15 12.69 | -116 51 58.48 | 501 divison |  | 1
8915BV | 15036BV | shay | Replacement | 2022-09-27 | Wood | OUCC | 60400008 | 34 14 58.30 | -116 51 58.20 | 650 mcalister |  | 1 | 2022-11-21
|  | Holcomb | Remediation | 2022-09-03 |  | IZ/BVES | 60400111 |  |  |  | 1
OCTOBER
10231BV | 15074BV | Shay 34kv | Replacement | 2022-10-01 | Wood | OUCC | 60400008 | 34.142736,-116.522902 |  | 804 Elm |  | 1
10284BV | 15073BV | shay | Replacement | 2022-10-05 | LWS | OUCC | 60400008 | 34' 14' 29.24" | (-116) 52' 29.04" | 584 elm |  | 1 | 2023-01-05
10296BV | 15071BV | shay | Replacement | 2022-10-05 | LWS | OUCC | 60400008 | 34' 14' 31.14" | (-116) 14' 31.14" | 584 elm |  | 1 | 2022-11-12
10219BV | 15054BV | shay | Replacement | 2022-10-06 | Wood | OUCC | 60400008 | 34' 14' 33.67" | (-116) 51' 58.58" | 1109 McAlister |  | 1
10209BV | 15055BV | shay | Replacement | 2022-10-06 | LWS | OUCC | 60400008 | 34' 14' 33.67" | (-116) 51' 58.58" | 1104 McAlister |  | 1
10187BV | 15056BV | shay | Replacement | 2022-10-06 | LWS | OUCC | 60400008 | 34' 14' 31.78" | (-116) 52' 00.25" | 42881 Cougar rd |  | 1
5211BV | 15319BV | Holcomb | Replacement | 2022-10-05 | Composite | BVES/IZ | 60400113 | 34.262431,-116.856694 |  | 1011 Mound |  | 1
8908BV | 15031BV | CASTLE GLEN |  | 2022-10-19 | LWS | OUCC | 60400008 | 34 15 05.72, -116.5159.4 |  | SUGARPINE RD |  |  | 2022-12-01
8909BV | 15032BV | CASTLE GLEN |  | 2022-10-19 | LWS | OUCC | 60400008 | 34 15 06.21, -116.5158.01 |  | PINEWOOD DR |  |  | 2022-11-21
BV11218 | 15009BV | CASTLE GLEN |  | 2022-10-24 | WOOD | OUCC | 60400008 | 34 15 37.02, -116.5158.43 |  | W. BIG BEAR BLVD |  |  | 2022-12-13
8691BV | 15010BV | CASTLE GLEN |  | 2022-10-24 | WOOD | OUCC | 60400008 | 34 15 35.54, -116.5158.37 |  | DIVISION DR
9379BV | 14999BV | CASTLE GLEN |  | 2022-10-24 | LWS | OUCC | 60400008 | 34 15 35.91, -116.5203.73 |  | W. BIG BEAR BLVD |  |  | 2022-12-19
8692BV | 15011BV | CASTLE GLEN |  | 2022-10-24 | WOOD | OUCC | 60400008 | 34 15 34.06, -116.5158.36 |  | DIVISION DR |  |  | 2022-12-19
5536BV | 15002BV | CASTLE GLEN |  | 2022-10-18 | LWS | OUCC | 60400008 | 34 15 32.79, -116.5159.92 |  | DIVISION DR
8693BV | 15012BV | CASTLE GLEN |  | 2022-10-18 | WOOD | OUCC | 60400008 | 34 15 32.77, -116.5158.3 |  | ROBINHOOD BLVD |  |  | 2022-12-20
8694BV | 15013BV | CASTLE GLEN |  | 2022-10-18 | WOOD | OUCC | 60400008 | 34 15 30.76, -116.5158.22 |  | RAINBOW BLVD
5350BV | 13428BV | ERWIN 4KV |  | 2022-10-25 | LWS | OUCC | 60400008 | 34.2575926, -116.8181.68 |  | 277 GREENSPOT BLVD |  |  | 2022-01-05
| 14773BV | ERWIN 4KV |  | 2022-10-25 | LWS | OUCC | 60400008 | 34.2526417, -116.81711.94 |  | GREENSPOT BLVD |  |  | 2022-11-21
| 14772BV | ERWIN 4KV |  | 2022-10-25 | LWS | OUCC | 60400008 | 34.2447306, -116.80979.17 |  | GREENSPOT BLVD |  |  | 2022-11-21
5681BV | 13432BV | ERWIN 4KV |  | 2022-10-25 | LWS | OUCC | 60400008 | 34 2552747, -116.25527.47 |  | 356 GREENSPOT BLVD |  |  | 2022-12-20
9762BV | 15001BV | CASTLE GLEN |  | 2022-10-21 | LWS | OUCC | 60400008 | 34 15 38.07, -116.5206.67 |  | W. BIG BEAR BLVD |  |  | 2022-11-21
9836BV | 15316BV | Shay | Replacement | 2022-10-31 | Composite | BVES/IZ | CAR HIT POLE | 34.2386028, -116.9220939 |  | Isaiah Z Design 40850 Pedder
NOVEMBER
| 14877BV | Lagonita | Install | 2022-11-01 | Wood | BVES/IZ | 60400120 |  |  | Isaiah Z Design 155 Round |  | 1
| 10258BV | Lagonita | Remediation | 2022-11-03 |  | BVES/IZ | 60400119 |  |  | Isaiah Z Design 152 Round | 1
DECEMBER
7302BV | 14906BV | Clubview | Replace |  | Wood | BVES/IZ |  | 34.2390412,-116.8548749 |  | 1248 Minton |  | 1
72221BV |  | Clubview | Remidiate |  |  | BVES/IZ |  | 34.2398760, -116.8556294 |  | 1212 Minton | 1
7301BV |  | Clubview | Remidiate |  |  | BVES/IZ |  | 34.2394023, -116.8551792 |  | 1236 Minton | 1
6106BV | 15315BV | Clubview | Replace |  | Composite | BVES/IZ |  | 34.2358328,-116.8542588 |  | 43474 Sheephorn |  | 1
5669BV |  | Clubview | Remidiate |  |  | BVES/IZ |  | 34.2361804,-116.8544608 |  | 43486 Sheephorn | 1
10259BV |  | Lagunitaz | Remidiate |  |  | BVES/IZ |  | 34.2519495,-116.9395755 |  | 160 Round | 1