## 2024
Order number | Program | Circuit ID | Circuit-segment ID number | Relevant wildfire risk score | Expected or Actual Start Date | Expected Completion Date | Length (in circuit miles) Covered Conductor | Length (in circuit miles) Underground Conductor | Length (in circuit miles) of Overhead Conductor to be Permanently Removed in 2023 and replaced by underground conductor | Length (in circuit miles) of overhead conductor to be permanently removed in 2023 and not replaced with covered conductor or underground conductor | Length (in circuit miles) of any other type of system hardening project to be installed in 2023 (if this is greater than zero, please describe the type of system hardening project).
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Clubview Circuit | OH_2935 | 3225.04 | Planned for 2024 | 2024-12-31 | 0.034526 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Clubview Circuit | OH_3244 | 3225.04 | Planned for 2024 | 2024-12-31 | 0.039312 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Clubview Circuit | OH_20659 | 3225.04 | Planned for 2024 | 2024-12-31 | 0.024581 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Clubview Circuit | OH_3300 | 3225.04 | Planned for 2024 | 2024-12-31 | 0.039783 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Clubview Circuit | OH_3302 | 3225.04 | Planned for 2024 | 2024-12-31 | 0.036529 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Clubview Circuit | OH_20658 | 3225.04 | Planned for 2024 | 2024-12-31 | 0.03115 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Clubview Circuit | OH_3253 | 3225.04 | Planned for 2024 | 2024-12-31 | 0.03131 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Clubview Circuit | OH_20653 | 3225.04 | Planned for 2024 | 2024-12-31 | 0.036385 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Clubview Circuit | OH_20657 | 3225.04 | Planned for 2024 | 2024-12-31 | 0.03325 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Clubview Circuit | OH_3298 | 3225.04 | Planned for 2024 | 2024-12-31 | 0.034151 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Clubview Circuit | OH_3266 | 3225.04 | Planned for 2024 | 2024-12-31 | 0.033099 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Clubview Circuit | OH_20660 | 3225.04 | Planned for 2024 | 2024-12-31 | 0.025275 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Clubview Circuit | OH_20654 | 3225.04 | Planned for 2024 | 2024-12-31 | 0.033258 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Clubview Circuit | OH_3395 | 3225.04 | Planned for 2024 | 2024-12-31 | 0.035514 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Clubview Circuit | OH_20662 | 3225.04 | Planned for 2024 | 2024-12-31 | 0.031738 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Clubview Circuit | OH_3391 | 3225.04 | Planned for 2024 | 2024-12-31 | 0.03242 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Clubview Circuit | OH_20671 | 3225.04 | Planned for 2024 | 2024-12-31 | 0.026719 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Clubview Circuit | OH_4043 | 3225.04 | Planned for 2024 | 2024-12-31 | 0.032926 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Clubview Circuit | OH_4074 | 3225.04 | Planned for 2024 | 2024-12-31 | 0.035991 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Clubview Circuit | OH_4533 | 3225.04 | Planned for 2024 | 2024-12-31 | 0.029941 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Clubview Circuit | OH_20684 | 3225.04 | Planned for 2024 | 2024-12-31 | 0.019705 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Clubview Circuit | OH_20682 | 3225.04 | Planned for 2024 | 2024-12-31 | 0.028915 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Clubview Circuit | OH_4488 | 3225.04 | Planned for 2024 | 2024-12-31 | 0.02749 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Clubview Circuit | OH_20677 | 3225.04 | Planned for 2024 | 2024-12-31 | 0.027656 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Clubview Circuit | OH_4496 | 3225.04 | Planned for 2024 | 2024-12-31 | 0.031163 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Clubview Circuit | OH_20675 | 3225.04 | Planned for 2024 | 2024-12-31 | 0.019248 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_11554 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.02158 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_11537 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.017698 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_20701 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.0095721 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_13432 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.019945 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_13433 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.027924 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_21038 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.023668 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_21039 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.027721 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_21040 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.028339 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_11520 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.036208 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_20691 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.023041 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_21041 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.025601 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_20689 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.029572 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_20690 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.018446 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_20688 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.021165 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_20687 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.025618 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_21042 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.02683 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_20685 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.031741 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_20681 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.026618 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_13422 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.03168 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_21043 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.026894 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_11533 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.020947 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_21044 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.021154 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_21046 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.027622 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_21047 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.027428 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_11502 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.028841 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_21048 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.01905 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_21049 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.028966 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_11541 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.036706 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_11510 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.033593 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_11514 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.02584 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_21051 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.031897 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_21052 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.031866 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_21053 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.035721 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_21054 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.033287 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_21055 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.025334 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_21056 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.033151 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_21057 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.034441 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_21058 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.033606 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_21059 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.036908 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_21060 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.031778 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_21061 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.031654 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_21062 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.036926 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_21063 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.040223 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_21064 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.025355 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_21065 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.039332 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_11547 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.033678 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_21066 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.020745 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Clubview Circuit | OH_11559 | 3225.04 | Planned for 2024 | 2024-12-31 | 0.027567 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Clubview Circuit | OH_11579 | 3225.04 | Planned for 2024 | 2024-12-31 | 0.028653 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Clubview Circuit | OH_20679 | 3225.04 | Planned for 2024 | 2024-12-31 | 0.018866 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Clubview Circuit | OH_4477 | 3225.04 | Planned for 2024 | 2024-12-31 | 0.027163 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_65540 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.043784 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_59650 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.044482 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_65539 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.035846 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_65538 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.032079 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_65537 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.067214 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_59646 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.033465 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_65541 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.033124 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_65542 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.054085 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_65543 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.043384 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_65544 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.034231 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_65545 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.039736 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_65546 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.038856 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_65547 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.045948 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_65548 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.044029 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_65549 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.036234 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_65550 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.042511 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_65551 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.03806 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_65552 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.038051 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_65553 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.027257 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_65554 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.031063 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_59598 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.036829 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_65555 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.034308 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_59628 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.024101 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_65556 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.026099 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_65557 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.027588 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_65558 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.035378 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_65926 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.026722 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_65559 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.038574 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_65560 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.040308 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_65561 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.029704 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_65562 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.024017 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_65563 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.046362 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_65564 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.033467 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_65925 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.032464 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_65565 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.034037 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_65566 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.044744 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_65567 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.047496 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_65568 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.036613 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_65569 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.029753 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_65570 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.034671 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_65571 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.03406 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_65572 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.030961 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_65573 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.035105 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_59600 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.034397 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_65574 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.032977 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_65400 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.032387 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_59597 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.039618 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_65397 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.039847 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_65398 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.037597 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_65399 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.037742 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_59590 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.048155 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_63188 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.025263 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_59621 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.041294 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_63181 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.052466 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_63182 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.051002 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_63183 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.0507 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_63184 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.013751 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_63185 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.029713 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_63186 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.033749 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_59629 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.037932 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_63187 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.037655 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_59594 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.021754 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_63190 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.030374 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_63191 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.021828 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_63192 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.039603 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_63193 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.033051 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_63194 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.023532 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_63195 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.034743 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_63196 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.031233 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_63197 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.029209 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_63198 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.040032 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_63199 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.030249 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_63200 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.037526 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_63201 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.029588 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_63202 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.027219 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_63203 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.040242 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_63209 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.036085 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_63204 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.042787 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_63208 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.037037 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_63207 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.018396 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_63205 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.031848 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_63224 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.032776 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_63225 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.014598 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_63226 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.028447 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_63227 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.028888 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_63228 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.022917 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_63229 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.03145 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_63230 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.038159 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_59625 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.036825 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_63231 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.035509 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_59640 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.19069 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_900145 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.024885 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH93528 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.0030278 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_53679 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.021764 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_53675 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.030126 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_53682 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.026371 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_53684 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.030075 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_27359 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.028722 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_53687 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.02737 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_53677 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.028233 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_53673 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.026056 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_31344 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.030052 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_37830 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.037818 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_53768 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.030843 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_53759 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.026762 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_53772 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.037779 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_37831 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.037916 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_53783 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.042528 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_53793 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.036407 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_53786 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.044309 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_27367 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.046549 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_53789 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.038347 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_53780 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.039853 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_53791 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.034268 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_53781 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.042892 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_37825 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.054335 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_53792 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.034387 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_53884 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.031501 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_33769 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.067659 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_53883 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.031918 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_53880 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.035712 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_53879 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.044778 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_53881 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.04382 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_53686 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.028416 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_53688 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.025744 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_53689 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.027642 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_53699 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.034992 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_53706 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.027418 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_53704 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.038985 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_53702 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.039472 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_53742 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.030021 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_53747 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.023737 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_53745 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.046389 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_53749 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.03216 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_53898 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.032256 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_53888 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.033763 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_53896 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.044977 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_53902 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.047546 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_53912 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.036945 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_53920 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.029955 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_27361 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.034464 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_54012 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.033984 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_54002 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.030828 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_53999 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.035353 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_53996 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.033873 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_53965 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.033656 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_37766 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.027232 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_53975 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.026792 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_53968 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.026547 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_53962 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.03395 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Holcomb Circuit | OH_54063 | 4746.15 | Planned for 2024 | 2024-12-31 | 0.02233 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62800 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.034501 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62578 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.043265 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62753 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.037843 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62607 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.038674 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62817 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.027713 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62650 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.03015 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62842 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.036694 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62913 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.030304 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_50929 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.038817 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62649 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.03032 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62772 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.030448 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_59233 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.034602 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62914 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.02383 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62528 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.033376 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62740 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.039965 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62773 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.021749 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_59232 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.030304 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62527 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.020261 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62529 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.037786 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62741 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.037842 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62500 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.033799 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62868 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.030146 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62886 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.0141 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62588 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.051011 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62796 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.051206 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_50915 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.051713 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62593 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.041182 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62482 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.026123 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_35613 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.018831 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62621 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.045685 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62897 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.032381 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62541 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.032975 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62937 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.013847 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62622 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.028445 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62808 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.028962 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62859 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.025105 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62570 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.039325 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62678 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.033251 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_36777 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.035883 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62935 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.035601 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Paradise Circuit | OH_57917 | 1809.55 | Planned for 2024 | 2024-12-31 | 0.031329 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Paradise Circuit | OH_57762 | 1809.55 | Planned for 2024 | 2024-12-31 | 0.023401 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Paradise Circuit | OH_57759 | 1809.55 | Planned for 2024 | 2024-12-31 | 0.027698 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Paradise Circuit | OH_57760 | 1809.55 | Planned for 2024 | 2024-12-31 | 0.03717 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Paradise Circuit | OH_57811 | 1809.55 | Planned for 2024 | 2024-12-31 | 0.027264 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Paradise Circuit | OH_57807 | 1809.55 | Planned for 2024 | 2024-12-31 | 0.028275 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Paradise Circuit | OH_47921 | 1809.55 | Planned for 2024 | 2024-12-31 | 0.029116 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Paradise Circuit | OH_57808 | 1809.55 | Planned for 2024 | 2024-12-31 | 0.019726 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Paradise Circuit | OH_57758 | 1809.55 | Planned for 2024 | 2024-12-31 | 0.036444 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Paradise Circuit | OH_57757 | 1809.55 | Planned for 2024 | 2024-12-31 | 0.033826 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Paradise Circuit | OH_47947 | 1809.55 | Planned for 2024 | 2024-12-31 | 0.034052 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Paradise Circuit | OH_57914 | 1809.55 | Planned for 2024 | 2024-12-31 | 0.033597 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Paradise Circuit | OH_57911 | 1809.55 | Planned for 2024 | 2024-12-31 | 0.015473 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Castle Glen Circuit | OH_56545 | 1483.32 | Planned for 2024 | 2024-12-31 | 0.026389 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Castle Glen Circuit | OH_33468 | 1483.32 | Planned for 2024 | 2024-12-31 | 0.028597 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Castle Glen Circuit | OH_30542 | 1483.32 | Planned for 2024 | 2024-12-31 | 0.029109 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Castle Glen Circuit | OH_33448 | 1483.32 | Planned for 2024 | 2024-12-31 | 0.028704 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | CountryClub Circuit | OH_28058 | N/A | Planned for 2024 | 2024-12-31 | 0.037518 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | CountryClub Circuit | OH_49518 | N/A | Planned for 2024 | 2024-12-31 | 0.031628 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | CountryClub Circuit | OH_49542 | N/A | Planned for 2024 | 2024-12-31 | 0.027699 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | CountryClub Circuit | OH_29488 | N/A | Planned for 2024 | 2024-12-31 | 0.032764 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | CountryClub Circuit | OH_29537 | N/A | Planned for 2024 | 2024-12-31 | 0.034302 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | CountryClub Circuit | OH_29912 | N/A | Planned for 2024 | 2024-12-31 | 0.028329 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | CountryClub Circuit | OH_29944 | N/A | Planned for 2024 | 2024-12-31 | 0.035028 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | CountryClub Circuit | OH_29918 | N/A | Planned for 2024 | 2024-12-31 | 0.024155 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | CountryClub Circuit | OH_49534 | N/A | Planned for 2024 | 2024-12-31 | 0.017743 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | CountryClub Circuit | OH_29924 | N/A | Planned for 2024 | 2024-12-31 | 0.031145 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | CountryClub Circuit | OH_49533 | N/A | Planned for 2024 | 2024-12-31 | 0.02256 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_65405 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.032697 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_65407 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.032877 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_59610 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.036487 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_65408 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.038099 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_65404 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.039023 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_65406 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.034859 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_65403 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.035383 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_65410 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.028054 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Baldwin Circuit | OH_65409 | 6890.98 | Planned for 2024 | 2024-12-31 | 0.030482 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_65474 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.024382 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_65460 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.029827 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_65476 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.028219 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_65471 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.028138 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_65469 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.028313 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_65466 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.028194 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_65464 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.029313 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_65479 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.028834 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_65478 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.027 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_65467 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.029498 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_65473 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.027575 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_65470 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.028616 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_59601 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.02889 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_65472 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.027779 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_65468 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.029226 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | Shay Circuit | OH_65465 | 3524.5 | Planned for 2024 | 2024-12-31 | 0.028322 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62725 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.01542 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62501 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.040612 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62629 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.03045 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62703 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.011914 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62554 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.020572 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62831 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.033674 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62551 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.04582 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62704 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.02961 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62583 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.03195 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62834 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.028791 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62721 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.029628 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62633 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.018114 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62710 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.022418 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62920 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.030106 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_39381 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.03582 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62522 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.022809 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62821 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.037793 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62726 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.038089 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62813 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.036061 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62917 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.037214 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62502 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.047402 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62592 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.04683 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62559 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.043161 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62711 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.040625 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62556 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.048768 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62511 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.040023 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62724 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.033949 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62496 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.047491 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62705 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.03984 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62598 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.042092 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62503 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.045229 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62851 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.034067 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62916 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.033886 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62498 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.03835 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62591 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.035756 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62736 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.034027 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62497 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.04402 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62918 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.03216 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62755 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.038614 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_40715 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.049134 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62719 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.049976 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62553 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.014359 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62585 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.02217 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62720 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.026974 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62520 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.03318 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62671 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.026988 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62514 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.030447 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62555 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.026191 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62471 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.042807 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62521 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.039574 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62722 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.03563 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62830 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.03324 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_40729 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.034082 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62584 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.036215 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62513 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.035511 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62479 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.033213 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62515 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.028924 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62512 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.038561 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62477 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.033328 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH_62718 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.029502 |  | N/A | N/A | N/A
WO Number has not be determined | GD_1, 8.1.2.1 Covered Conductor Installation | North Shore Circuit | OH96994 | 6717.24 | Planned for 2024 | 2024-12-31 | 0.023696 |  | N/A | N/A | N/A